## project_progress_tracker
PROJECT SCHEDULE TEMPLATE
PROJECT NAME | Emergency Department Database and Analysis System |  |  | PROJECT MANAGER | Team 22 (Suk Jin Mun, Xiaobai Li, Shaobo Chen)
PROJECT DELIVERABLE | Final Project - DS 5110 |  |  | COURSE | DS 5110: Introduction to Data Management and Processing
SCOPE STATEMENT | Database design, statistical modeling, Flask API, data visualization |  |  | TEAM | Suk Jin (Backend/API), Xiaobai (Frontend/Viz), Shaobo (Database)
START DATE | END DATE | OVERALL PROGRESS
Sep-25 | Nov-29 | 25%
TASK NAME | ASSIGNED TO | START DATE | END DATE | STATUS | COMMENTS
Task 1.0: Form team and assign roles: Establish Team 22 with three members and define clear role boundaries. S... | All | Sep Week 1 | Sep Week 2 | Complete | Suk Jin (backend API developer) Xiaobai (frontend developer) Shaobo (database architect)
Task 2.0: Select project topic: Initial selection of hospital database project focusing on general operations.... | All | Sep Week 1 | Sep Week 3 | Complete | Hospital database for operations
Task 3.0: Submit iteration 01: Compile and submit initial project proposal including team composition, prelimi... | Suk Jin | Sep Week 3 | Sep Week 4 | Complete | Submitted on Canvas
Task 4.0: Review course materials: Comprehensive review of DS5110 course content from weeks 1-6 covering datab... | All | Oct Week 1 | Oct Week 3 | Complete | Weeks 1-6 lectures and reading Ch3-Ch4
Task 5.0: Review professor feedback: Analyze iteration 01 feedback indicating project scope was too broad with... | All | Oct Week 2 | Oct Week 2 | Complete | Topic too broad - need specific focus
Task 6.0: Refine project scope: Narrow focus from general hospital operations to specific Emergency Department... | All | Oct Week 2 | Oct Week 3 | Complete | ED triage classification and wait time
Task 7.0: Design database schema: Create initial conceptual schema for ED database including core entities (pa... | Shaobo | Oct Week 3 | Oct Week 4 | Complete | Initial schema design in 3NF
Task 8.0: Write 3-page report: Compose comprehensive Overleaf LaTeX document addressing all iteration 02 requi... | All | Oct Week 3 | Oct Week 4 | Complete | Addresses all iteration 02 requirements
Task 9.0: Create progress tracker: Design and implement CSV-based project progress tracker with fields for tas... | Suk Jin | Oct Week 4 | Oct Week 4 | Complete | This file
Task 10.0: Setup GitHub repo: Initialize GitHub repository at https://github.com/SukjinMun/DS5110-Final-Project... | Suk Jin | Oct Week 4 | Oct Week 4 | Complete | Public repo with README and CSV
Task 11.0: Submit iteration 02: Package all iteration 02 deliverables including 3-page PDF report generated fro... | Suk Jin | Oct Week 4 | Oct Week 4 | Complete | Submitted on Canvas
Task 12.0: Design and implement SQLite schema: Transform conceptual schema into physical implementation using S... | Shaobo | Iter3 Week 1 | Iter3 Week 2 | Not Started | Normalized schema with constraints and ERD
Task 13.0: Build data generation script: Develop Python script using NumPy and Pandas to generate realistic sim... | Shaobo | Iter3 Week 1 | Iter3 Week 2 | Not Started | Simulated ED patient visits with https://data.gov/ distributions
Task 14.0: Populate database: Develop ETL pipeline script to load generated CSV data into SQLite database. Crea... | Shaobo | Iter3 Week 2 | Iter3 Week 3 | Not Started | Load generated data into SQLite via ETL pipeline
Task 15.0: Validate data integrity: Perform comprehensive data integrity validation on populated database. Writ... | Shaobo | Iter3 Week 2 | Iter3 Week 3 | Not Started
Task 16.0: Document ETL pipeline: Create comprehensive documentation for entire ETL process from data generatio... | Shaobo | Iter3 Week 2 | Iter3 Week 3 | Not Started
Task 16.5: Create ETL process flowcharts and diagrams: Design visual flowcharts showing ETL pipeline steps from... | Xiaobai | Iter3 Week 2 | Iter3 Week 3 | Not Started
Task 17.0: Develop SQL analytical queries: Write at least 8 complex SQL queries demonstrating database analytic... | Shaobo | Iter3 Week 2 | Iter3 Week 3 | Not Started | At least 8 analytical queries: patient counts by urgency average wait times staff workload visit trends repeat patients case ratios resource utilization time-series
Task 17.6: Document SQL query results and create summary visualizations: Execute Shaobo analytical SQL queries ... | Xiaobai | Iter3 Week 2 | Iter3 Week 3 | Not Started | SQL query visualization support
Task 17.7: Review and approve database work for GitHub: Review Shaobo completed database schema, data generatio... | Suk Jin | Iter3 Week 2 | Iter3 Week 3 | Not Started
Task 17.5: Study course materials for EDA and visualization: Review lecture materials and in-class work example... | Xiaobai | Iter3 Week 1 | Iter3 Week 2 | Not Started | Study materials for EDA work
Task 18.5: Create data quality visualizations: Develop visualizations showing data quality metrics from validat... | Xiaobai | Iter3 Week 2 | Iter3 Week 3 | Not Started
Task 18.0: Exploratory data analysis: Perform initial EDA on generated ED data using Pandas and Jupyter Noteboo... | Xiaobai | Iter3 Week 3 | Iter3 Week 3 | Not Started | Summary stats and distributions
Task 19.0: Create initial visualizations: Develop exploratory visualizations using Matplotlib, Seaborn, and Plo... | Xiaobai | Iter3 Week 3 | Iter3 Week 3 | Not Started | Time series and correlation plots
Task 19.5: Study course materials for statistical modeling: Review reading assignments and lecture materials re... | Suk Jin | Iter3 Week 1 | Iter3 Week 2 | Not Started | Reading and studying modeling theory
Task 19.6: Complete InClassWork_04 modeling exercises: Work through InClassWork_04 which directly practices ski... | Suk Jin | Iter3 Week 2 | Iter3 Week 3 | Not Started | Hands-on modeling practice
Task 19.7: Develop model prototypes with sample data: Create actual working prototypes of the three model types... | Suk Jin | Iter3 Week 2 | Iter3 Week 3 | Not Started | Create working model prototypes
Task 19.8: Design and document modeling approach: Create detailed design documents specifying the exact approac... | Suk Jin | Iter3 Week 2 | Iter3 Week 3 | Not Started | Design modeling specifications
Task 19.62: Implement business logic module early: Develop business_logic.py module with validation and calculat... | Suk Jin | Iter3 Week 2 | Iter3 Week 3 | Not Started | Build business logic module - independent development
Task 19.9: Design backend API architecture and database integration layer: Study Shaobo's completed database sc... | Suk Jin | Iter3 Week 3 | Iter3 Week 3 | Not Started | Backend API and database integration design - depends on Task 12
Task 19.95: Review and approve analysis work for GitHub: Review Xiaobai completed EDA notebooks and visualizatio... | Suk Jin | Iter3 Week 3 | Iter3 Week 3 | Not Started | Git repository management - admin approval required
Task 20.0: Mid-project checkpoint meeting (COLLABORATIVE - all team members work together): Conduct comprehensi... | All | Iter3 Week 3 | Iter3 Week 3 | Not Started | Collaborative checkpoint - evaluate progress and plan Flask development
Task 21.0: Data cleaning and validation: Perform additional data quality checks and cleaning beyond initial ETL... | Shaobo | Iter4 Week 1 | Iter4 Week 1 | Not Started | Handle missing values validate ranges (HR 40-200 temp 95-105) remove duplicates standardize formats enforce referential integrity
Task 22.0: Train classification models for triage urgency prediction: Develop and compare multiple classificati... | Suk Jin | Iter4 Week 1 | Iter4 Week 2 | Complete | 2025-11-10
Task 23.0: Train regression models for wait time prediction: Build linear regression models to predict continuo... | Suk Jin | Iter4 Week 1 | Iter4 Week 2 | Complete | 2025-11-10
Task 24.0: Train Poisson regression for daily visit count modeling: Apply Generalized Linear Model (GLM) with P... | Suk Jin | Iter4 Week 2 | Iter4 Week 2 | Complete | 2025-11-10
Task 25.0: Implement business logic and validation rules: Develop Python module implementing business logic for... | Suk Jin | Iter4 Week 1 | Iter4 Week 2 | Not Started | Data validation and integrity checks
Task 26.0: Calculate statistical indicators and metrics: Develop functions to compute key performance indicator... | Suk Jin | Iter4 Week 2 | Iter4 Week 3 | Not Started | Conversion rates averages automatic calculations
Task 27.0: Model evaluation and performance assessment: Conduct comprehensive evaluation of all trained statist... | All | Iter4 Week 2 | Iter4 Week 3 | Complete | 2025-11-10
Task 27.5: PySpark large-scale data analysis (OPTIONAL - advanced analysis): Load ED data into PySpark for dist... | Suk Jin or Shaobo | Iter4 Week 2 | Iter4 Week 3 | Not Started | Optional PySpark distributed analysis
Task 28.0: Create model visualization and interpretation plots: Develop visualizations to interpret and communi... | Xiaobai | Iter4 Week 2 | Iter4 Week 3 | Not Started | Feature importance and prediction plots
Task 29.0: Design Flask API endpoints: Design and implement RESTful API using Flask framework to serve as integ... | Suk Jin | Iter4 Week 1 | Iter4 Week 2 | Complete | 2025-11-10
Task 29.5: Implement database access layer: Create data access layer separating database operations from API en... | Suk Jin | Iter4 Week 2 | Iter4 Week 3 | Not Started | Backend executes SQL queries on behalf of frontend
Task 30.0: Build Flask frontend web interface: Develop web-based user interface using Flask templates (Jinja2),... | Xiaobai | Iter4 Week 1 | Iter4 Week 3 | Not Started | Web UI with forms calling backend API and chart display
Task 31.0: Compile final report content: Collaboratively write comprehensive final project report documenting e... | All | Iter5 Week 1 | Iter5 Week 1 | Not Started | Methods results recommendations
Task 32.0: Format final report with figures in Overleaf: Transfer compiled report content to Overleaf LaTeX doc... | Xiaobai | Iter5 Week 1 | Iter5 Week 2 | Not Started | Overleaf LaTeX formatting
Task 33.0: Create presentation slides for class: Develop compelling presentation (15-20 slides) for class deliv... | Xiaobai | Iter5 Week 1 | Iter5 Week 2 | Not Started | Class presentation materials
Task 34.0: Finalize GitHub repository for submission: Prepare GitHub repository for final evaluation ensuring p... | Suk Jin | Iter5 Week 2 | Iter5 Week 2 | Not Started | README documentation code organization
Task 35.0: Practice presentation delivery: Conduct team rehearsal of class presentation to ensure smooth delive... | All | Iter5 Week 2 | Iter5 Week 2 | Not Started | Rehearse delivery and timing
Task 36.0: Submit final deliverables: Package and submit all final project deliverables according to course req... | Suk Jin | Iter5 Week 2 | Iter5 Week 2 | Not Started | Report slides code submission
Task 37.0: Present to class: Deliver final project presentation to DS5110 class demonstrating completed work an... | All | Iter5 Week 2 | Iter5 Week 2 | Not Started | Class presentation and demo